## EXAMPLE - Stakeholder Analysis
Stakeholder Analysis Template Example
Project Name |  |  |  |  | Project Manager |  | Date | Version
Process Improvement Initiative |  |  |  |  | Romy Bailey |  | 01/01/20XX | 1.0.1
Name or Group | Role / Position | Predisposition | Anticipated Involvement | Decision Maker (Yes / No) | Anticipated Issues | Impact | Motivation | Expectations of Exchange | Milestones | Activities | Date Due | Status
Jonathon Wong | Project Sponsor | Supportive | Regular updates and key decisions | Yes | Concerns about timeline | Decision Authority | Successful project completion | Timely updates on project progress | Define (Initial scope), Control (Project closure) | Approving project charter, monitoring progress | 03/15/XX | Not Started
Mateus Tobin | Operations Manager | Neutral | Involved in process design and improvement | No | Resource constraints | Will Be Affected | Streamlined operations | Regular meetings, involvement in process design | Measure (Data collection), Improve (Process redesign) | Reviewing process maps, providing operational insights | 03/01/XX | Not Started
|  | Ambivalent |  |  |  | Impacts Outcome
Resistant
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Stakeholder Analysis
Stakeholder Analysis Template
Project Name |  |  |  |  | Project Manager |  | Date | Version
Name or Group | Role / Position | Predisposition | Anticipated Involvement | Decision Maker (Yes / No) | Anticipated Issues | Impact | Motivation | Expectations of Exchange | Milestones | Activities | Date Due | Status

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
Influence | Predisposition | Impact | Type | Status | Yes / No
Low | Supportive | Decision Authority | Internal | Not Started | Yes
Medium | Neutral | Impacts Outcome | External | In Progress | No
High | Ambivalent | Will Be Affected | Direct | Complete
| Resistant |  | Indirect | Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.