## EXAMPLE Project Status Report
Krista Ahmed
Project Status Report Template Example
Project Name | Learning Platform Rollout | Project Code | PSR-2032-LXP
Project Manager | Krista Ahmed | Date of Status Entry | 2032-03-27
Period Covered | March 20-27, 2032 | Projected Date of Completion | 2032-08-15
Project Status This Week
Overal Project Status | POTENTIAL RISKS / DELAYS | *Enter information here about the overall status and highlights.
Summary | The project remains on schedule, but early-stage content validation has revealed inconsistencies across regional modules. Vendor response times on LMS integration requests have slowed, posing a moderate risk to the April milestone. Development on mobile accessibility features is ahead of plan, which may offset downstream testing delays.
Decisions Needed
Owner / Requester | Decision Description | Deadline | Status
Krista Ahmed | Approve revised scope for onboarding modules. | 2032-04-01 | In Review
Tech Ops Lead | Confirm internal QA resources for the mid-April sprint. | 2032-03-30 | Pending
MILESTONES | Final content sets for three regional modules are 90% complete; full delivery remains possible by March 29 but depends on the final feedback cycle. The LMS integration environment is on track for deployment by April 5, with internal testing scheduled to begin two days later. QA activities for core modules will start on April 22; scope adjustments may require minor test plan updates. The pilot launch remains scheduled for June 10, contingent on completing the May user acceptance testing window. The overall go-live date of August 15 is unchanged. We will reassess in April following milestone two and early QA outcomes.
Project Components
Component | Status | Owner / Team | Notes
Budget | On Budget | Finance / PM | Vendor invoices remain consistent with projections.
Resources | Limited | HR / Tech Ops | QA resources for Sprint 4 are not yet confirmed.
Timeline | Potential Risks / Delays | Project Manager | Risk from content review and integration delays.
Scope | Changing | Product Team | Added two onboarding modules at the regional team's request.
Performance Metrics
KPI | Current Value | Previous Value | Trend Indicator | Change
Sprint Completion Rate | 91% | 93% | ↓ Slightly Down | -2%
Budget Utilization | 54% | 46% | ↑ On Track | 8%
QA Test Case Pass Rate | N/A | N/A | Scheduled Q2 | #VALUE!
Content Review Completion | 72% | 58% | ↑ Strong Progress | 14%
Work Accomplished
Task Number | Description | Owner / Team | Reception
T-204 | Content module QA checklist finalized | Quality Team | Approved
T-205 | Integration API schema updated | Dev Team | Delivered on time
T-206 | Localization testing on three regions started | Localization Team | In Progress
T-207 | Content module QA checklist finalized | Quality Team | Approved
T-208 | Integration API schema updated | Dev Team | Delivered on time
Risks and Roadblocks
Risk Number | Description | Owner / Team | Fix
R-001 | Delay in LMS API response from vendor | Integration Lead | Escalated to vendor; temporary stub in use
R-002 | QA staffing shortfall for Sprint 4 | HR / QA Lead | Additional contractor requested
Project Risk Scoring
Risk No. | Probability (1–5) | Impact (1–5) | Score (Probability x Impact)
R-001 | 4 | 4 | 16
R-002 | 3 | 5 | 15
0
0
Highlights and Key Takeaways |  | Bullets of great work, who owns what, where teams are pivoting, feedback received during the week, etc.
Early completion of accessibility modules by the UI/UX team. Integration schema finalized two days ahead of Sprint 3 kickoff. Content QA flagged inconsistencies early—mitigation is now underway. Regional team leadership has approved the scope update for the onboarding flow.
Project Schedule
Week Number | Status | Details
Week 12 | POTENTIAL RISKS / DELAYS | Content approval delays could affect Sprint 4 readiness.
Week 11 | ON TRACK | Sprint 3 tasks completed; team velocity within the expected range.
Project Timeline
CLICK HERE TO CREATE IN SMARTSHEET
MILESTONE 1
Regional content completion – due March 29
MILESTONE 2
Integration environment live – due April 5
MILESTONE 3
Details
MILESTONE 4
Details
MILESTONE 5
Details
CURRENT TIMELINE POSITION
03/27/2032
ROADBLOCK 1
API latency from LMS vendor causing integration lag.
ROADBLOCK 2
Details
PROJECT START DATE
01/10/2032
PROJECT END DATE
08/15/2032

## BLANK Project Status Report
Project Status Report Template
Project Name |  | Project Code
Project Manager |  | Date of Status Entry
Period Covered |  | Projected Date of Completion
Project Status This Week
Overal Project Status | POTENTIAL RISKS / DELAYS | *Enter information here about the overall status and highlights.
Summary
Decisions Needed
Owner / Requester | Decision Description | Deadline | Status
MILESTONES
Project Components
Component | Status | Owner / Team | Notes
Budget | On Budget
Resources | Limited
Timeline | Potential Risks / Delays
Scope | Changing
Performance Metrics
KPI | Current Value | Previous Value | Trend Indicator | Change
Sprint Completion Rate |  |  | ↓ Slightly Down | 0%
Budget Utilization |  |  | ↑ On Track | 0%
QA Test Case Pass Rate |  |  | Scheduled Q2 | 0%
Content Review Completion |  |  | ↑ Strong Progress | 0%
Work Accomplished
Task Number | Description | Owner / Team | Reception
Risks and Roadblocks
Risk Number | Description | Owner / Team | Fix
Project Risk Scoring
Risk No. | Probability (1–5) | Impact (1–5) | Score (Probability x Impact)
0
0
0
0
Highlights and Key Takeaways |  | Bullets of great work, who owns what, where teams are pivoting, feedback received during the week, etc.
Project Schedule
Week Number | Status | Details
POTENTIAL RISKS / DELAYS
ON TRACK
ROADBLOCK / OVERAGE
Project Timeline
MILESTONE 1
Details
MILESTONE 2
Details
MILESTONE 3
Details
MILESTONE 4
Details
MILESTONE 5
Details
CURRENT TIMELINE POSITION
00/00/0000
ROADBLOCK 1
Details
ROADBLOCK 2
Details
PROJECT START DATE
00/00/0000
PROJECT END DATE
00/00/0000

## Dropdown Keys - DO NOT DELETE
DROPDOWN KEYS - DO NOT DELETE
OVERALL STATUS KEY | BUDGET KEY | GENERAL STATUS KEY | Trend Indicator
ROADBLOCK / OVERAGE | On Budget | DELAYED | ↓ Slightly Down
POTENTIAL RISKS / DELAYS | Limited | NOT STARTED | Scheduled Q2
ON TRACK | Potential Risks / Delays | ON HOLD | ↑ On Track
| Changing | COMPLETE | ↑ Strong Progress
IN PROGRESS

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.